## Sheet1
Week | Backend | Frontend | Estimation of difficulty(1 for easy, 3 for hard)
2022-09-22 | build system | build system | 3
2022-09-29 | build system | build system | 3
2022-10-06 | build system | build system | 3
2022-10-13 | test continuous delivery | test continuous delivery | 2
2022-10-20 | test continuous delivery | test continuous delivery | 2
2022-10-27 | test continuous delivery | test continuous delivery | 2
2022-11-03 | API that returns no data | connects to an API | 1
2022-11-10 | API with test data | connects to an API | 1
2022-11-17 | API with test data | connects to an API | 1
2022-11-24 | Backend ready for QA | Frontend ready for QA | 2
2022-12-01 | Check deploy status | check deploy status | 1
2022-12-08 | Test prediction result | test and browse url | 1
| Goals | Goals
| ML API | Deployed on Azure
| Logging | Python
Formulas:
Week = [Week, row above]+7